## Sheet1
KADUNA STATE ROAD AGENCY (KADRA) - 2024 PROJECTS
S/N | CONTRACT/PROJECT NAME | CONTRACTOR | CONTRACT NO | PROCURING ENTITY | CONTRACT DATE (PROJECT INITIATION) | CONTRACT DURATION | CONTRACT PRICE/BUDGET | PROJECT PROGRESS STATUS
1 | Reconstruction and upgrading of Asphaltic Access Roads within the Old Panteka Markrt, Kaduna State | (M/S Uplift Engineering Nig. Ltd) | KDS/PPA/GHPROJ.31/2024/VOL./41 | Kaduna State Roads Agency (KADRA) | 29 April,2024 | 14 WEEKS | 2308660008.4 | Completed
2 | Construction of a 15km Access Road connecting Kasuwan Maganin to Wusar in Kajuru LGA, Kaduna state | (M/S Stonegate Engineering and Quarries Ltd) | KADRA/CE/PCRD/CP/05/2024/VOL.II/008 | Kaduna State Roads Agency (KADRA) | 27 May,2024 | 12 Months | 5246054089.15 | Completed
3 | Construction of a 5.8km Access Road from Gwaraji to Wusar connecting Igabi and Kajuru LGAs of Kaduna State | (M/S Ancob Nigeria Ltd) | KADRA/CE/RD/CP/05/2024/VOLII/009 | Kaduna State Roads Agency (KADRA) | 27May,2024 | 12Months | 1738426422 | Completed
4 | Reconstruction of a 6km Asphaltic Road from Rafin Guza to Hayin Naiya To Malalin Gabas To Kukumaki, linking the existing on-going road construction at KASU Permanent Si(M/S Ancob Nigeria Ltd)(M/S Ancob Nigeria Ltd)e, Kaduna State V | (M/S Thinklab Group | KADRA/CE/RD/05/2024/VOL.II/010 | Kaduna State Roads Agency (KADRA) | 28 May,2024 | 12Months | 4542267232.84 | Completed
5 | Construction of a 13km Access Road connecting Turawa to Dinya Through DA’A, Kurungpa and Kadage in Soba LGA, Kaduna StateReconstruction of a 6km Asphaltic Road from Rafin Guza to Hayin Naiya To Malalin Gabas To Kukumaki, linking the existing on-going road construction at KASU Permanent Site, Kaduna State (M/S Thinklab Group | M/S Triacta Nigeria Ltd) | KDS/CE/RD/KADRA/24/VOL.II 007 | Kaduna State Roads Agency (KADRA) | 28 May,2024 | 12Months | 4807335084.5 | ONGOING
6 | Completion of Abandon Pan Drive to Kachia Road (220m), Kaduna ( | ( M/S Green-Max International Ltd) | KDS/KADRA/PROJ.01/2024/V.I | Kaduna State Roads Agency (KADRA) | 20 May,2024 | 14 WEEKS | 245769986 | Completed
7 | Reconstruction of 1.4km water drainage road from Patric Yakowa way to Maigero junction, Upgrading and maintenance of 3.15km, Maigero Narayi junction road | (M/S Powerhill Construction Ltd) | KDS/KADRA/PROJ.01/2024/VOLI | Kaduna State Roads Agency (KADRA) | 20 May,2024 | 6 Months | 678693844.5 | Completed
8 | Construction of A 148KM Ring Access Road from Danbushiya Junction to Danhonou through Keke A, Keke B, Keke Makera, Doka Mai Jamaa and Sabon Gero In Millenium City, Chikun LGA, Kaduna State | (M/S Thinklab Group Ltd) | KDS/PPA/GH/PROJ.31/2024/VOLI/55 | Kaduna State Roads Agency (KADRA) | 23 July,2024 | 18 Months | 12282800531.54 | Completed
9 | Reconstruction of 21.95km Road Madauchi to Kafanchan through Madakiya, including A Spur to Matsirga waterfalls, Linking Jema’a to Zangon kataf LGAs, Kaduna State (M/S Stonegate Engineering and Quarries Nig. Ltd | (M/S Stonegate Engineering and Quarries Nig. Lt | KADARA/CE/RD/CP/08/2024 | Kaduna State Roads Agency (KADRA) | 23 July,2024 | 18 Months | 12966686136.55 | Completed
10 | Re-Construction of a 35.6km Road from Bagoma to Gagumi through Unguwan Fari, Idi Labo, Awaro, Tashan Keji and Sabon Layi, in Birnin Gwari LGA, Kaduna State | (M/S Thinklab Group Ltd) | KDS/PPA/GH/PROJ.31/2024/VOLI/56 | Kaduna State Roads Agency (KADRA) | 23 July,2024 | 18 Months | 14503964471.47 | Ongoing
11 | Re- Construction of A21.85km Pambeguwa to Kauru through Kahuta, linking Kubau to Kauru LGAs, Kaduna State | (M/S Farmtract Nig. Ltd) | KADRA/PPA/GH/PROJ.31/2024/VOL.I/59 | Kaduna State Roads Agency (KADRA) | 23 July, 2024 | 18 Months | 8649265461.5 | Completed
12 | Emergency construction of a 3-Cell box culvert at Tudai Community, Lere LGA, Kaduna State | (M/S Green-Max International Ltd) | KDS/PPA/GH/PROJ.1/2025/VOL.I/204 | Kaduna State Roads Agency (KADRA) | 10 July,2025 | 3 Months | 349768551.8 | Ongoing
13 | General Rehabilitation and Repair of collapsed Culvert on Abuja Road, Rigasa, Repair of Faked Retaining walls on College Road by Gwamna Road and Drainage construction at No.3 Road ‘A’ Unguwan Rimi , Kaduna State | (M/S Green-Max International Ltd) | KDS/PPA/KADRA/PROJ.31/2024 | Kaduna State Roads Agency (KADRA) | 2024-07-03 | 3 Months | 288489319.15 | Completed
14 | Reconstruction and upgrading of Ja Abdulkadir and Bissau Roads Ung. Rimi, Kaduna State | M/S Mother cat Ltd) | KADRA/CE/RD/CP/07/2024/VOL.II/004 | Kaduna State Roads Agency (KADRA) | 3 July 2024 | 12 Months | 1153574817.6 | Completed
15 | Completion of Sultan-Surame Road connecting Shehu Laminu Road, Unguwan Rimi, Kaduna | (M/S Mothercat Ltd) | KDS/PPA/GH/PROJ.31/2024/VOL.II/77 | Kaduna State Roads Agency (KADRA) | 2024-09-11 | 3 Months | 2181292186.4 | Completed
16 | Completion of a 1.7km, 300 Beds Hospital, Crescent Road with Spurs and Exit link at Anguwa Ma’aji, Millennium City, Chikun LGA, Kaduna state | (M/S Power Hill Construction Ltd) | KDS/PPA/GH/PROJ.31/2024/VOL.II/76 | Kaduna State Roads Agency (KADRA) | 2024-09-11 | 3 Months | 1291470387.91 | Completed
17 | Reconstruction and Expansion of Kaduna Metropolis: Kakuri Road, Ogbadu/Kamsalem, Murtala Crescent/Danladi, Danazumi Road, Ohinoyi and Umaru Gwandu Roads) | (M/S Mothercat Ltd) | KDS/PPA/GH/PROJ.31/2024/VOL.II/94 | Kaduna State Roads Agency (KADRA) | 2024-09-18 | 3 Months | 1232337017.05 | Ongoing
18 | Construction and Upgrading of a 1.3km Estate Access Road to State House Lodges, Kawo, Kaduna State | M/S Green-Max International Ltd) | KDS/PPA/GH/PROJ.31/2024/VOL.II/77 | Kaduna State Roads Agency (KADRA) | 2024-09-11 | 3Months | 592352383.43 | Ongoing
19 | Emergency Repairs of Ahmadu Bello Way, Stadium-Station Roundabouts | (M/S Mothercat Nig. Ltd) | KDS/PPA/PPA/KADRA/PROJ.01/VOL.I/56 | Kaduna State Roads Agency (KADRA) | 3rd Oct-2024 | 8 Weeks | 2482882531.5 | Completed
20 | Construction of 2x3 Three-Cell Box Culvert at Ikulu, off Fadan Kamantan, Zangon Kataf LGA, Kaduna State () | (M/S Farmtrac Nig. Ltd) | KADRA/CE/RD/CP/07/2024/VOLII/008 | Kaduna State Roads Agency (KADRA) | 2024-11-11 | 18 Months | 161524932.28 | Completed
21 | Emergency Construction of an Additional Single Cell 3m by 3m Reinforced Concrete Culvert, Stone Pitching of Culvert Embankment, Provision of Filter bed, Riprap and Reinstatement of the Failed Pavement at Marjire, Lere LGA Kaduna State | (M/S Farmtrac Nig. Ltd) | KDS/PPA/GH/PROJ.31/2024/VOL.II/105 | Kaduna State Roads Agency (KADRA) | 2024-11-11 | 8 Months | 168551095.39 | Completed
22 | Construction of Additional Box Culvert, Reconstruction of Collapsed Elements of Existing Triple Cell Box Culvert and Reinstatement of Washout Along Access Road to Hayin Malam Bello, Rigasa in Igabi LGA Kaduna | (M/S Farmtrac Nig. Ltd) | KDS/PPA/KADRA/2024/PROJ.01/VOL.I/102 | Kaduna State Roads Agency (KADRA) | 2024-11-11 | 18 Months | 264980344.85 | Completed
23 | Completion of Rabah Road Carriage Way from U/Kanawa to Rigasa Train Station, Kaduna State | M/S CCECC Nig. Ltd) | KDS/PPA/GH/PROJ.31/2024 | Kaduna State Roads Agency (KADRA) | 3rd Dec-2024 | 12 Months | 20295018230.31 | Completed
24 | Completion of the Proposed Dual Carriage from NEPA Round About to U/Rimi Bridge and Hospital Road Kafanchan, Kaduna State | (M/S Rafali Nig. Ltd) | KDS/PPA/GH/PROJ.31/2024 | Kaduna State Roads Agency (KADRA) | 3rd Dec-2024 | 6 Months | 9367905341.87 | Completed
25 | Construction and Upgrading of Abdullahi Yero Road, Abakpa Kaduna ( | (M/S Farmtrac Nig. Ltd) | KDS/PPA/GH/PROJ.31/2024/VOL.II/112 | Kaduna State Roads Agency (KADRA) | 2024-12-10 | 6 Months | 392254291.74 | Completed
26 | Emergency Repairs Failed Road section and Patching of 7.3KM Jere to S.C.C Road At Bwari Junction, Kagarko LGA, Kaduna State | (M/S Green Max International Ltd) | KDS/PPA/GH/PROJ.31/2024/VOL.II/143 | Kaduna State Roads Agency (KADRA) | 2024-12-18 | 3 Months | 283423481.25 | Ongoing
KADUNA STATE FACILITIES MANAGEMENT AGENCY (KADFAMA) - 2024 PROJECTS
S/N | CONTRACT/PROJECT NAME | CONTRACTOR | CONTRACT NO | PROCURING ENTITY | CONTRACT DATE (PROJECT INITIATION) | CONTRACT DURATION | CONTRACT PRICE/BUDGET | PROJECT STATUS
1 | Remodeling of Kaduna State Government Lodge, Abuja | M/S Blacline Architects Limited, | KDS/KADFAMA/Proj.01/167/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-02-22 | 8 Weeks | 262323371 | Completed
2 | Reconstruction of 204m Length Collapse Fence at Ranchers Bees Stadium, Kaduna | M/S H3D International Concept Ltd. | KDS/KADFAMA/Proj.01/167/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-03-26 | 8 Weeks | 26388412.13 | Completed
3 | Completion of the on-going Renovation of State House (Hassan Usman Katsina House) Kawo | M/S H3D International Concept Ltd. | KDS/KADFAMA/Proj.01/168/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-03-26 | 16 Weeks | 989231257.79 | Completed
4 | Renovation and Upgrading of Special Protection Unit (SPU) at Millenium City Chikun LGA, Kaduna | M/S Radcom Nigeria Limited, Kaduna. | KDS/KADFAMA/Proj.01/169/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-05-27 | 8 Weeks | 395256843 | Completed
5 | Proposed Renovation of Government Lodge at Race Course, Kaduna | M/S Digitize Archy Limited | KDS/KADFAMA/Proj.01/170/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-06-20 | 8 Weeks | 112691061.36 | Completed
6 | Renovationnof Administrative and Confeence Room at State Pension Bureau | M/S JTEE MS Limited | KDS/KADFAMA/Proj.01/172/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-08-21 | 8 Weeks | 14774974.69 | Completed
7 | Completion/Remodeling of Kaduna State Primary Healthcare Board, Tafawa Balewa Way, Kaduna | M/S Multiple A. Integrated Services Limited | KDS/KADFAMA/Proj.01/173/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-09-23 | 7 Months | 1183789883.33 | Completed
8 | Repairs and Renovation of Kaduna Investment Promotion Agency (KADIPA) | M/S Mufaj Multi ServicesLimited | KDS/KADFAMA/Proj.01/174/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-10-10 | 8 Weeks | 30151122.82 | Completed
9 | Renovation and Refushment of Kaduna State Traffic Law Enforcement Authority (KASTLEA) | M/S Al-amin Engineering Services Limited | KDS/KADFAMA/Proj.01/176/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-11-14 | 12 Weeks | 66915777.31 | Completed
10 | Renovation and Upgrading of 3 Units of Government Essential Houses State ''LOT A'' | M/S Bitts and Barrels Nigeria Limited | KDS/KADFAMA/Proj.01/183/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-12-17 | 3 Months | 406674029.27 | Completed
11 | Renovation and Upgrading of 3 Units of Government Essential House States ''LOT B'' | M/S Digibuild Nigeria Limited | KDS/KADFAMA/Proj.01/184/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-12-17 | 3 Months | 439917834.45 | Completed
12 | Renovation and Upgrading of 1 Unit of Government Essential House at Shehu Laminu U/Rimi, Kaduna ''LOT C'' | M/S Dakes Global Concept Limited | KDS/KADFAMA/Proj.01/185/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-12-17 | 3 Months | 401409160.17 | Completed
13 | Provision of Security Infrastructure for some Selected Schools Within Kaduna State | M/S Digitized Archy Limited | KDS/KADFAMA/Proj.01/186/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-12-17 | 3 Months | 425782344.85 | Completed
14 | Provision of Security Infrastructure in some Prone Areas Within the State | M/S Nerida Construction Limited | KDS/KADFAMA/Proj.01/187/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-12-18 | 3 Months | 483567855.5 | Completed
15 | Renivation of LGEA Primary School Sabon Gayan 2 and LGEA Primary School Idon Hanya Lot 5 | M/S Nextbrains Technologies | KDS/KADFAMA/Proj.01/222/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-03-26 | 2 Weeks | 336247402.29 | Completed
16 | Renivation of LGEA Primary School Tamba Maigana and LGEA Primary School Limanci Kwaire,Zaria City Lot 6 | M/S Nextbrains Technologies | KDS/KADFAMA/Proj.01/224/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-05-27 | 2 Weeks | 420997909.08 | Completed
17 | Renivation of LGEA Primary School Kako Zaria Kewaye and LGEA Primary School Limanci Hatin Gada Lot 7 | M/S Nextbrains Technologies | KDS/KADFAMA/Proj.01/225/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-06-20 | 2 Weeks | 366466034.64 | Completed
18 | Renovation of LGEA Primary School Kurmin Bomo, Basawa and LGEA Primary School Yarkasuwa Lot 8 | M/S Nextbrains Technologies | KDS/KADFAMA/Proj.01/226/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-08-21 | 2 Weeks | 365443398.6 | Completed
19 | Renovation of LGEA Primary School Kurmin Bomo, Basawa and LGEA Primary School Yarkasuwa Lot 8 | M/S FZ Ellesmere Global Limited | KDS/KADFAMA/Proj.01/227/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-08-21 | 2 Weeks | 348043691.75 | Completed
20 | Renovation of LGEA Primary School Pala and LGEA Primary School Garu Lot 10 | M/S FZ Ellesmere Global Limited | KDS/KADFAMA/Proj.01/228/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-09-23 | 2 Weeks | 395346151.35 | Completed
21 | Renovation of LGEA Primary School Bargi and LGEA Primary School Kutal Lot 11 | M/S FZ Ellesmere Global Limited | KDS/KADFAMA/Proj.01/229/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-10-10 | 3 Months | 333812751.34 | Completed
22 | Renovation of LGEA Primary School Faki 2, LGEA Model Primary School Chikka and LGEA UBE Primary School Bandi Majidadi Lot 12 | M/S FZ Ellesmere Global Limited | KDS/KADFAMA/Proj.01/230/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-11-14 | 3 Months | 495835632.28 | Completed
23 | Renovation of LGEA Primary School Yaji Ankawa and LGEA Primary School Janjala Lot 13 | M/S FZ Ellesmere Global Limited | KDS/KADFAMA/Proj.01/231/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-11-14 | 3 Months | 353860895.92 | Completed
24 | Renovation of LGEA Primary School Kagal Zonkwa and LGEA Primary School Kukui Lot 14 | M/S FZ Ellesmere Global Limited | KDS/KADFAMA/Proj.01/232/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-03-26 | 3 Months | 352816391.96 | Completed
25 | Renovation of LGEA Primary School Kamfanin Mamman Yarwa, Tabanni Ward Birnin Gwari, LGEA Primary School Maganda and LGEA Primary School Yelwa Maibene Lot 15 | M/S FZ Ellesmere Global Limited | KDS/KADFAMA/Proj.01/233/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-05-27 | 3 Months | 482334404.9 | Completed
26 | Renovation of LGEA Primary School Maidugri Road Lot 16 | M/S Nakaka Global Concept | KDS/KADFAMA/Proj.01/234/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-06-20 | 7 Weeks | 187610842.53 | Completed
27 | Renovation of LGEA Primary School Malali Lot 17 | M/S Inbred Investment Limited | KDS/KADFAMA/Proj.01/235/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-08-21 | 8 Weeks | 207302143.55 | Completed
28 | Renovation of LGEA Primary School Sabchem, LGEA Primary School Kurmin Masara Zaman Dabo Lot 18 | M/S E.M Guga's Limited | KDS/KADFAMA/Proj.01/236/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-08-21 | 8 Weeks | 390290451.01 | Completed
29 | Renovation of LGEA Primary School Aduan Lot 19 | M/S Soks International Investment Ltd | KDS/KADFAMA/Proj.01/237/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-09-23 | 8 Weeks | 135367227.04 | Completed
30 | Renovation of LGEA Primary School Pambegua Lot 20 | M/S Sandstone Consult Services Ltd | KDS/KADFAMA/Proj.01/238/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-10-10 | 8 Weeks | 196393633.5 | Completed
31 | Renovation of LGEA Central Primary School Madakiya II | M/S Macodem Properties's Limited | KDS/KADFAMA/Proj.01/239/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-11-14 | 8 Weeks | 148385336.01 | Completed
32 | Renovation of LGEA Model Primary School Igabi | M/S Gsm Arena And It Solution | KDS/KADFAMA/Proj.01/240/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-11-14 | 12 Weeks | 136939276.95 | Completed
33 | Renovation of LGEA Primary School Chawai Road Unguwan Sunusi | M/S Nakaka Homes Properties | KDS/KADFAMA/Proj.01/241/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-03-26 | 12 Weeks | 189203638.12 | Completed
34 | Renovation of LGEA Primary School Kawo, Kaduna | M/S Jeniks Projects's Limited | KDS/KADFAMA/Proj.01/242/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-05-27 | 12 Weeks | 217657966.47 | Completed
35 | Renovation of LGEA Primary School Katsina Road | M/S Jeniks Projects's Limited | KDS/KADFAMA/Proj.01/243/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-06-20 | 8 Weeks | 225014604.3 | Completed
36 | Repairs and Renovation of Administrative Blk, Office Blk, Computer Lab, General Store, Rehabilitation Centre Blk, Board Secretary Blk, Gate House, Generator House & External Works at Ministry of Human Services and Social Development, Kaduna (Lot 1) | M/S Ijoa Multi Global Services | KDS/KADFAMA/Proj.01/244/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-08-21 | 8 Weeks | 304591816.33 | Completed
37 | Repairs and Renovation of Maintenance Office Blk, Conference Hall Blk, Laundry, Store, Principal Accountant Blk, Laundry & Mosque at Ministry of Human Services and Social Development, Kaduna (Lot 2) | M/S Global IB Investment Co. Ltd. | KDS/KADFAMA/Proj.01/245/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-08-21 | 12 Weeks | 200765349.21 | Completed
38 | Renovation of Collapsed Fence at Queen FM Zaria, Kaduna | M/S Maggot General Services. | KDS/KADFAMA/Proj.01/244/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-09-23 | 12 Weeks | 32459123 | Completed
39 | Repairs and Renovation of Public Library at Kofar Doka Zaria | M/S Shamronix Nigeria Limited | KDS/KADFAMA/Proj.01/246/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-10-10 | 12 Weeks | 377231134.63 | Completed
40 | Remodeling and Upgrading of NYSC Camp College Road Kurmin Mashi, Kaduna | M/S Mahfu Integrated Solution Ltd | KDS/KADFAMA/Proj.01/247/vol 1/2024 | Kaduna State Facilities Management Agency (KADFAMA) | 2024-11-14 | 18 Weeks | 467654879 | Completed
MINISTRY OF HOUSING AND URBAN DEVELOPMENT (MHUD) - 2024 PROJECTS
S/N | CONTRACT/PROJECT NAME | CONTRACTOR | CONTRACT NO | PROCURING ENTITY | CONTRACT DATE (PROJECT INITIATION) | CONTRACT DURATION | CONTRACT PRICE/BUDGET | PROJECT PROGRESS STATUS
1 | Construction of Skills Acquisation Centre at Tudun Biri Community, Kaduna State | M/S Power Hill Nig. Ltd. | KDS/MUHD/HD/004/9/2019/VOL.II | Ministry of Housing and Urband Development (MHUD) | 2024-03-20 | 3 Months | 168560950.5 | Completed
2 | Construction of Perimeter Fencing and Access Road on Plot No. 403730 Kassarami/C12/Gwagwada | M/S Bartford Engineering Services | KDS/MHUD/PB/CT.353/2/2024/VOL.I | Ministry of Housing and Urband Development (MHUD) | 2024-08-12 | 3 Months | 550017470.99 | Completed
3 | Construction of Kofan Gayan Gate in Zaria LGA | M/S RUK Mina Nigeria Ltd. | KDS/MHUD/PB/004/9/2019/VOL.II | Ministry of Housing and Urband Development (MHUD) | 2024-08-29 | 3 Months | 29750275.63 | Completed
4 | Construction of ICT Center at Old Panteka Market Kaduna South Local Government Area, Kaduna State | M/S Pioneer Global Innovation Limited | KDS/MHUD/PB/CT.353/2/2024/VOL.I | Ministry of Housing and Urband Development (MHUD) | 2024-05-02 | 3 Months | 216257587.54 | Completed
5 | Construction of Primary Health Care Center at Tudun Biri Community, Kaduna State | M/S Team Work Constrution & Engineering Service | KDS/MHUD/002/2024 | Ministry of Housing and Urband Development (MHUD) | 2024-03-19 | 3 Months | 224450670 | Ongoing
6 | Rehabilitation and furnishing of Giwa General Hospital in Giwa LGA, kaduna state | M/S Grand Legend Plus Nigeria Ltd. | KDS/MHUD/005/2024 | Ministry of Housing and Urband Development (MHUD) | 15.04.2024 | 12 Weeks | 1488956021.16 | Ongoing
7 | Rehabilitation and furnishing of Ikara General Hospital, Ikara LGA, kaduna state | M/S M & W Resources Ltd. | KDS/MHUD/004/2024 | Ministry of Housing and Urband Development (MHUD) | 15.04.2024 | 12 Weeks | 851288774.11 | Ongoing
8 | Rehabilitation and furnishing of Patrick Ibrahim Yakowa Memorial General Hospital, Kafanchan, Jamaa LGA, Kaduna State | M/S Uplift Engineering Nigeria Ltd. | KDS/MHUD/006/2024 | Ministry of Housing and Urband Development (MHUD) | 15.04.2024 | 12 Weeks | 1602858707.81 | Ongoing
10 | Rehabilitation and upgrade of maigana general hospital, Soba, Kaduna State | M/S ASG Solar Techniq Ltd. | MOH/PU/2020/476/vol.I | Ministry of Housing and Urband Development (MHUD) | 22.04.2024 | 12 Weeks | 202255719.13 | Ongoing
11 | Renovation of general hospital, Rigasa, Igabi Local government area, Kaduna | M/S Dan Gudey Resources Ltd. | MOH/PU/2020/475/vol.I | Ministry of Housing and Urband Development (MHUD) | 22.04.2024 | 12 Weeks | 650416551.85 | Ongoing
12 | Proposed construction of accident and emergency block at general hospital, Rigasa, Igabi LGA, Kaduna | M/S Dan Gudey Resources Ltd. | MOH/PU/2020/487/vol.I | Ministry of Housing and Urband Development (MHUD) | 22.04.2024 | 12 Weeks | 77363293.06 | Ongoing
13 | Renovation and upgrade of general hospital, Gwantu, Sanga LGA, Kaduna State | M/S Damalum Nigeria Ltd. | MOH/PU/2020/477/vol.I | Ministry of Housing and Urband Development (MHUD) | 22.04.2024 | 12 Weeks | 262121084.4 | Ongoing
14 | Proposed Rehabilitation of general hospital, Gwantu at Sanga LGA, Kaduna State | M/S AmaSkills Ltd | MOH/PU/2019/444 | Ministry of Housing and Urband Development (MHUD) | 22.04.2024 | 12 Weeks | 185953372.03 | Ongoing
15 | Proposed Rehabilitation and Furnishing of Sabon Tasha General Hospital, Chikun LGA, Kaduna | M/S Brixly Creed Ltd. | KDS/MHUD/0009/2024 | Ministry of Housing and Urband Development (MHUD) | 04.07.2024 | 12 Weeks | 1580841122.72 | Ongoing
16 | The Rehabilitation, Upgrading and Furnishing of Lere General Hospital, Saminaka, Lere LGA | M/S 1365 Investment Ltd. | KDS/MHUD/0010/2024 | Ministry of Housing and Urband Development (MHUD) | 2024-07-22 | 12 Weeks | 1732002143.19 | Ongoing
17 | The Rehabilitation, Upgrading and Furnishing of Kachia General Hospital, Kachia LGA | M/S Purple Rose Ltd. | KDS/MHUD/0010/2024 | Ministry of Housing and Urband Development (MHUD) | 2024-07-22 | 12 Weeks | 1429441784.12 | Ongoing
Kaduna State Water Corporation, (KADSWAC)
S/N | CONTRACT/PROJECT NAME | CONTRACTOR | CONTRACT NO | PROCURING ENTITY | CONTRACT DATE (PROJECT INITIATION) | CONTRACT DURATION | CONTRACT PRICE/BUDGET | PROJECT PROGRESS STATUS
1 | Rehabilitation of Kaduna North New 150MLD and Kaduna North old 90MLD Water works and Booster Stations | M/S Allworth Engineering Ltd. | SURWASH/KADSWAC/SSS/2024/LOT.1 | KADSWAC | 2024-12-05 | 18 months | 7210827869 | ONGOING
2 | Rehabilitation of Kaduna South 27MLD Water works and Booster Stations and Rehabilitation of Distribution of System in Kaduna | M/S J Patel & Sons Nig. Ltd | SURWASH/KADSWAC/SSS/2024/2/LOT.2 | KADSWAC | 2024-12-05 | 18 months | 6144734003 | ONGOING
3 | Rehabilitation of Zaria New 150MLD, Zaria 50MLD and Zaria 10MLD Water works and Booster Stations and Rehabilitation of Distribution System in Zaria | M/S Mothercat Nig. Ltd | SURWASH/KADSWAC/SSS/2024/2/LOT.3 | KADSWAC | 2024-12-05 | 18 months | 3392334083.28 | ONGOING
4 | Design and Supervision of Works Contracts of Kaduna Metropolitan Service Area and Zaria Regional Scheme Service Area | M/S Enviplan International Ltd. | SURWASH/KADSWAS/SSS/2024/2/LOT.4 | KADSWAC | 2024-12-05 | 18 months | 667320000 | ONGOING
5 | Construction of Transmission Mains and Distribution Systems at Basawa, Hunkuyi, Kudan and Makarfi | M/S Mothercat Limited | KDS/PPA/KADSWAC/Vol.III | KADSWAC | 2025-02-27 | 11 months | 33562529961.02 | ONGOING
Kaduna Sate Primary Health Care Board
S/N | CONTRACT/PROJECT NAME | CONTRACTOR | CONTRACT NO | PROCURING ENTITY | CONTRACT DATE (PROJECT INITIATION) | CONTRACT DURATION | CONTRACT PRICE/BUDGET | PROJECT PROGRESS STATUS
1 | Remodelling, reconstruction and expansion of kaduna state primary health care board (SPHCB) Headquaters | M/S Lubell Nig. Ltd. | KDSPHCB/ADM/405/Vol.I | Kaduna State Primary Healthcare Board | 2023-10-22 | 36 Weeks | 797150090.07 | COMPLETED
2 | Upgrading/Renovation and Revitalization of PHC Kwasallo ward, sabo LGA and PHC Rimin Doko ,Kwara Ward, Zaria LGA. | M/S Unique Executive Services Nig Ltd. | KDSPHCB/SF/ADM/443/Vol.II | Kaduna State Primary Healthcare Board | 2024-11-25 | 28 Weeks | 89881051.61 | COMPLETED
3 | Upgrading/Renovation and Revitalization of PHC Shika Ward,Giwa LGA &PHC Miyeeti Allah,Rigasa ward,Igabi LGA | .M/S Mu'asfat Int'l Services Nig,Ltd | KDSPHCB/SF/ADM/443/Vol.III | Kaduna State Primary Healthcare Board | 2024-09-30 | 28 Weeks | 117558088.65 | COMPLETED
4 | Upgrading,Renovation and Revitalization of PHC Kaura ward,Kaura LGA & Ancha Makaranta,Ninzo west ward, Sanga LGA | M/S Pioneer Global Innovation Ltd | KDSPHCB/SF/ADM/443/Vol.IV | Kaduna State Primary Healthcare Board | 3o-Sep-24 | 28 Weeks | 111051636.1 | COMPLETED
MINISTRY OF BUSINESS INNOVATION AND TECHNOLOGY 2023 PROJECT
S/N | Contractor Name | Contract number | Contract/Project name | Procuring entity name | Contract date (project initiation) | Contract duration | Contract price / Budget | Project progress today (if available
1 | J-Patel and Sons Nigeria Limited | KDS/DG/PIRD/11 | Construction of Skills and Technology Acquisition City Rigachikun | MBIT | 24/11/2023 | 24 Weeks | 5890256706.57 | Ongoing
2 | Westfield Global Contruction Limited | KDS/DG/MBT/23 | Construction of Skills and Technology Acquisition City Soba | MBIT | 18 /12/2023 | 24 Weeks | 3713508608.62 | Ongoing
3 | Westfield Global Contruction Limited | KDS/DG/MBT/23 | Construction of Skills and Technology Acquisition City Samaru Kataf | MBIT | 18 /12/2023 | 24 Weeks | 3713508608.62 | Ongoing
4 | Kadalux Global Resource Limited | MBIT/2022/1448 | Construction of Collapsed Perimeter Fence, Construction of Storm Water Drainage, Repairs of Workshop and ICT/CBT of COSDEC Kachia | MBIT | 2022-06-10 | 3 Weeks | 32526731.14 | Ongoing
MINISTRY OF PUBLIC WORKS AND INFRASTRUCTURE
S/N | Contractor Name | Contract number | Contract/Project name | Procuring entity name | Contract date (project initiation) | Contract duration | Contract price / Budget | Project progress today (if available
| Thru-Put Pow | KDS/PPA/MPWI/PROJ.1/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Damuco Integrated Services Ltd. | KDS/PPA/MPWI/PROJ.2/VOL.I | CONSTRUCTION OF TOILET FACILITY IN HEALTH CLINIC | MPWI | 2023-11-28 | 6 Wekks | 5128834 | Completed
| AMS Multi Dynamic Consultancy Ltd. | KDS/PPA/MPWI/PROJ.3/VOL.I | UPGRADE OF THE TOILET FACILITIES AND CONSTRUCTION OF BOREHOLE | MPWI | 2023-11-28 | 6 Wekks | 8908724.8 | Completed
| Amhad worldwide Enterprise | KDS/PPA/MPWI/PROJ.4/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Amhad worldwide Enterprise | KDS/PPA/MPWI/PROJ.5/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Walfad International Investment Ltd | KDS/PPA/MPWI/PROJ.6/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Walfad International Investment Ltd | KDS/PPA/MPWI/PROJ.7/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Ovos Consult | KDS/PPA/MPWI/PROJ.8/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Ovos Consult | KDS/PPA/MPWI/PROJ.9/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Ovos Consult | KDS/PPA/MPWI/PROJ.10/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Yusra Ventures Ltd. | KDS/PPA/MPWI/PROJ.11/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Walfad International Investment Ltd | KDS/PPA/MPWI/PROJ.12/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Walfad International Investment Ltd | KDS/PPA/MPWI/PROJ.13/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| AD City One | KDS/PPA/MPWI/PROJ.14/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Aufaz | KDS/PPA/MPWI/PROJ.15/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Embee Tukur Ltd | KDS/PPA/MPWI/PROJ.16/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Embee Tukur Ltd | KDS/PPA/MPWI/PROJ.17/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Bellfan Concept Nigeria Ltd | KDS/PPA/MPWI/PROJ.18/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Bellfan Concept Nigeria Ltd | KDS/PPA/MPWI/PROJ.19/VOL.I | CONSTRUCTION OF MINI SOLAR POWERED BOREHOLE AND VIP LATRINES | MPWI | 2023-11-28 | 6 Wekks | 12497504.8 | Completed
| Sha-Um Trans Africa Ltd. | KDS/PPA/MPWI/PROJ.20/VOL.I | CONSTRUCTION OF TOILET FACILITY AND HAND PUMP BOREHOLE | MPWI | 2023-11-28 | 6 Wekks | 8908724.8 | Completed
| Dairma Construction Company Ltd. | KDS/PPA/MPWI/PROJ.21/VOL.I | CONSTRUCTION OF TOILET FACILITY AND HAND PUMP BOREHOLE | MPWI | 2023-11-28 | 6 Wekks | 8908724.8 | Completed
| Rashfan Solidarc Intergrated Rsources Ltd. | KDS/PPA/MPWI/PROJ.22/VOL.I | CONSTRUCTION OF TOILET FACILITY AND HAND PUMP BOREHOLE | MPWI | 2023-11-28 | 6 Wekks | 8908724.8 | Completed
| Usmania Global Resources Limited | KDS/PPA/MPWI/PROJ.23/VOL.I | CONSTRUCTION OF TOILET FACILITY AND HAND PUMP BOREHOLE | MPWI | 2023-11-28 | 6 Wekks | 8908724.8 | Completed
| North Steam International Investment Ltd. | KDS/PPA/MPWI/PROJ.24/VOL.I | CONSTRUCTION OF TOILET FACILITY AND HAND PUMP BOREHOLE | MPWI | 2023-11-28 | 6 Wekks | 8908724.8 | Completed
| Ankelii Ene Company Limited | KDS/PPA/MPWI/PROJ.25/VOL.I | REHABILITATION AND UPGRADE OF SANITATION FACILITY AND CONSTRUCTION OF MINI SOLAR | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Centric Logistics | KDS/PPA/MPWI/PROJ.26/VOL.I | CONSTRUCTION OF SANITATION FACILITY AND UPGRADE OF HANDPUMP BOREHOLE TO SOLAR POWERED BOREHOLE | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Centric Logistics | KDS/PPA/MPWI/PROJ.27/VOL.I | CONSTRUCTION OF SANITATION FACILITY AND UPGRADE OF HANDPUMP BOREHOLE TO SOLAR POWERED BOREHOLE | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Centric Logistics | KDS/PPA/MPWI/PROJ.2/VOL.I | RENOVATION/UPGRADE OF SANITATION FACILITY AND MINI SOLAR SCHEME | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Centric Logistics | KDS/PPA/MPWI/PROJ.28/VOL.I | CONSTRUCTION OF SANITATION FACILITY AND UPGRADE OF HANDPUMP BOREHOLE TO SOLAR POWERED BOREHOLE | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Treznergy Solutions Limited | KDS/PPA/MPWI/PROJ.29/VOL.I | REHABILITATION AND UPGRADE OF SANITATION FACILITY AND CONSTRUCTION OF MINI SOLAR | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Treznergy Solutions Limited | KDS/PPA/MPWI/PROJ.30/VOL.I | CONSTRUCTION OF VIP LATRINES WITH RETICULATION OF WATER SUPPLY | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Treznergy Solutions Limited | KDS/PPA/MPWI/PROJ.31/VOL.I | CONSTRUCTION OF TOILET FACILITY AND REHABILITATION OF HAND PUMP FACILITY | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Sanbaco Construction Company Limited | KDS/PPA/MPWI/PROJ.32/VOL.I | CONSTRUCTION OF VIP LATRINES AND REHABILITATION OF SOLAR SCHEME | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Sanbaco Construction Company Limited | KDS/PPA/MPWI/PROJ.33/VOL.I | REHABILITATION OF SANITATION FACILITY AND MINI SOLAR SCHEME | MPWI | 2023-11-28 | 6 Wekks | 12401203.88 | Completed
| Diepre Intergrated Synergy Limited | KDS/PPA/MPWI/PROJ.34/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Kina Home Limited | KDS/PPA/MPWI/PROJ.35/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Creative Transnationation International Investment | KDS/PPA/MPWI/PROJ.36/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| HMZ Signature Limited | KDS/PPA/MPWI/PROJ.37/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Bellfan Concept Nigeria Ltd | KDS/PPA/MPWI/PROJ.38/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Embee Tukur Ltd | KDS/PPA/MPWI/PROJ.39/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Dandutse Global | KDS/PPA/MPWI/PROJ.40/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Dandutse Global | KDS/PPA/MPWI/PROJ.41/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| HMZ Signature Limited | KDS/PPA/MPWI/PROJ.42/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Sukash Synergy Ltd. | KDS/PPA/MPWI/PROJ.43/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Ampere Global | KDS/PPA/MPWI/PROJ.45/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Ame | KDS/PPA/MPWI/PROJ.46/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| AD City One | KDS/PPA/MPWI/PROJ.47/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Aufaz | KDS/PPA/MPWI/PROJ.48/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Gada Grand Nigeria Ltd | KDS/PPA/MPWI/PROJ.49/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| MN Ataj | KDS/PPA/MPWI/PROJ.50/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Walfad International Investment Ltd | KDS/PPA/MPWI/PROJ.51/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Bidvest Nigeria Ltd | KDS/PPA/MPWI/PROJ.52/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| MN Ataj | KDS/PPA/MPWI/PROJ.53/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| MN Ataj | KDS/PPA/MPWI/PROJ.54/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Bidvest Nigeria Ltd | KDS/PPA/MPWI/PROJ.55/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Qtys Plus Projects Limited | KDS/PPA/MPWI/PROJ.2/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Qtys Plus Projects Limited | KDS/PPA/MPWI/PROJ.56/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Decker & Brown | KDS/PPA/MPWI/PROJ.57/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Decker & Brown | KDS/PPA/MPWI/PROJ.58/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Jabbama Services Nig. Ltd | KDS/PPA/MPWI/PROJ.59/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Jabbama Services Nig. Ltd | KDS/PPA/MPWI/PROJ.60/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| Purple Rose | KDS/PPA/MPWI/PROJ.61/VOL.I | CONSTRUCTION/REHABILITATION AND UPGRADE OF WATER AND SANITATION FACILITIES | MPWI | 2023-11-28 | 6 Wekks | 22077001 | Completed
| M/S Farmtrac Nig. Ltd | KDS/PPA/MPWI/PROJ.62/VOL.I | Construction of a 0.963km road at TPO 1186B, NTA layout kinshasa road ungwan rimi, Kaduna State | MPWI | 2024-02-19 | 6 Wekks | 230101292.25 | Completed
| M/S Farmtrac Nig. Ltd | KDS/PPA/MPWI/PROJ.63/VOL.I | Construction of a 2.07km road at TPO 1383, Rimi College layout, Ungwan Rimi, Kaduna State | MPWI | 2024-02-19 | 14 weeks. | 454234329.1 | Completed
| M/S Bleet Ltd. | KDS/PPA/MPWI/PROJ.64/VOL.I | Construction of a 500m fence at TPO 1383, Rimi Collage Layout, Ungwan Rimi | MPWI | 2024-02-19 | 14 weeks. | 44582690 | Completed
| M/S Bwalco Nig. Ltd. | KDS/PPA/MPWI/PROJ.2/VOL.I | Construction of a 5.525km Asphaltic Road from Airport Road to Tudun Biri Community, Kaduna State | MPWI | 2024-03-18 | 14 weeks. | 3098116854.25 | Completed
| M/S Farmtrac Nig. Ltd | KDS/PPA/MPWI/PROJ.65/VOL.I | Construction of Ungwan Muazu Township Roads (Phase 1 & 2) | MPWI | 2024-05-25 | 14 weeks. | 1382200278.09 | Completed
| M/S Graycoy Engineering Ltd. | KDS/PPA/MPWI/PROJ.66/VOL.I | Construction of Kwagiri Kusom-Wasa Road Jema'a Local Government Request for Review and Certification of Variation of Price (VOP) | MPWI | 2024-09-19 | 14 weeks. | 2292006906.7 | Completed
| M/S ASF Alliance Limited | KDS/PPA/MPWI/PROJ.67/VOL.I | Renovation of Main Building at Governor's Residence,Sir Kashim Ibrahim House, Kaduna (LOT5) | MPWI | 2025-05-06 | 8 Weeks | 498883113 | Completed
| M/S Echis Materials & Quantities Limited | KDS/PPA/MPWI/PROJ.68/VOL.I | Renovation of Underground Facility at Governors Residence Sir, Kashim Ibrahim House, Kaduna | MPWI | 2025-07-09 | 8 Weeks | 87421956.08 | Completed